# Drift-Aware Label Creation and Monitoring Plan for SAR Marine Plastic Detection

## Executive summary

This report proposes a practical, drift-aware plan to create reliable Sentinel-1 SAR labels by transferring optical detections (Sentinel-2 / Planet-class) across a time gap using a physical drift (transport) model with uncertainty, then converting the resulting search region into SAR annotations via a combination of cross-modal matching, weak supervision, and human-in-the-loop review. The plan is grounded in the provided research proposal (2025) and progress update (19 Feb 2026), whose central constraint is the lack of directly usable SAR-labeled training data (notably due to issues accessing the MIREIA SAR label locations), despite having substantial optical-labeled evidence. (Proposal: Pretorius, 2025; Progress update: Pretorius, 2026)

The technical core is a Lagrangian particle ensemble drift engine (recommended: OpenDrift[1]) that uses gridded surface currents and winds (e.g., Copernicus Marine Service[2] products) to propagate debris-patch locations from optical timestamp t0 to SAR timestamp t1, producing either (a) an uncertainty ellipse / bounding box or (b) a probability raster overlay to guide SAR label creation. [3]

In parallel, this report specifies an ML “drift” monitoring track in the data/label/concept drift sense: distributional changes in SAR inputs, predicted masks, and delayed ground-truth performance. This monitoring layer is recommended to be implemented with a combination of Alibi Detect[4] (image/time-series drift tests), River[5] (online drift detectors such as ADWIN/EDDM on scalar monitoring signals), and optionally NannyML[6] for performance estimation concepts where labels are delayed (noting it is primarily tabular-focused and likely requires adaptation for segmentation). [7]

A staged implementation plan (weeks), resourcing estimates, risks/mitigations, and success criteria are provided, as well as comparison tables of candidate drift engines and labeling/monitoring toolchains. The recommended “best-bet” strategy is a hybrid: (1) small, high-quality “anchor” labels from controlled/field observations, (2) scalable drift-aware optical→SAR transfer for volume, and (3) iterative improvement through active learning and label-quality audits. [8]

## Project context distilled from the proposal and progress update

The proposal authored by Joshua Pretorius[9] under supervision of Bolelang Sibolla[10] and Shelley Haupt[11] (at University of Pretoria[12] and CSIR[13]) targets a SAR-based pipeline to detect floating marine debris/plastics in the South African Exclusive Economic Zone[14], with study focus near Durban[15], Gqeberha[16], and Cape Town[17]. (Proposal: Pretorius, 2025)

### Label targets and definitions inferred from the documents

The intended ML task (as described in the proposal) is best interpreted as semantic segmentation of “marine debris / plastic slick” vs “non-debris background” in image patches, with optional extension to multi-class “confusers” (e.g., wakes, foam, algae) to reduce false positives. This interpretation aligns with the proposal’s emphasis on a U-Net segmentation architecture and on leveraging datasets such as MARIDA (which explicitly includes co-occurring sea features). (Proposal: Pretorius, 2025) [18]

Because the progress update highlights the absence of “true positives for debris drift matching training” in the locally created dataset so far, the operational labeling problem becomes: create sufficiently accurate SAR labels that can fine-tune a SAR segmentation model, while handling real ocean transport uncertainty across sensor time gaps. (Progress update: Pretorius, 2026)

### Data sources and planned feature stack

The project’s sensor/data stack is stable and well supported by official sources:

- Sentinel-1 SAR (Level-1 SLC), motivated by need for higher-fidelity SAR information (including phase-derived products such as coherence) and nominal IW-mode resolution on the order of 5 m × 20 m. [19]

- Sentinel-2 MSI Level-2A optical imagery (13 bands, 10–60 m, BOA reflectance) to establish an optical baseline and support cross-sensor label seeding. [20]

- Biophysical forcing from Copernicus Marine: global physics analysis/forecast currents (1/12° class product) and hourly sea-surface wind fields (0.125° product). [21]

The proposal also specifies derived features such as SAR backscatter (VV/VH), texture measures, and polarimetric descriptors; plus optical indices such as the Floating Debris Index (FDI) and a Plastic Index (PI) for optical identification/validation support. [22] (Proposal: Pretorius, 2025)

### Current models, performance metrics, and known issues

Current model direction (from the documents): - A U-Net family segmentation model with a self-supervised pretraining strategy. (Proposal: Pretorius, 2025)
- Incorporation of attention gating is explicitly considered (proposal), consistent with the established “Attention U-Net” approach. [23]
- Self-supervised pretraining references SSL4EO-style multimodal corpora for Sentinel-1/2 representation learning, plus a second stage of domain-specific SSL on marine SAR scenes. [24] (Proposal: Pretorius, 2025)

Performance metrics: - The progress update proposes validating the drift model using RMSE between predicted and detected patch locations in optical imagery (where detection is more established). (Progress update: Pretorius, 2026)
- The proposal does not lock down final segmentation metrics, but for semantic segmentation in remote sensing, standard practice is IoU/mIoU, Dice/F1, precision/recall, plus calibration measures when probabilistic outputs are used (recommended in this report). [25]

Known issues (critical): - The progress update states the project “counted heavily” on MIREIA because it is the only dataset directly applicable to SAR labeling, but SAR labels “can’t be obtained,” creating a major bottleneck. (Progress update: Pretorius, 2026) [26]
- Sentinel-1 constellation realities matter operationally: Sentinel-1B is end-of-mission, while Sentinel-1A remains operational and Sentinel-1C has entered operations (with occasional operational unavailability events). [27]
- SAR SLC product sizes are large; typical IW SLC products are reported around ~8 GB/product in literature—relevant to storage and compute planning. [28]

## Survey of relevant methods and tooling

This section separates two meanings of “drift” that must be handled simultaneously:

- Transport drift (physical drift): ocean advection/dispersion of debris patches used to transfer labels between sensors/times.

- ML drift (data/concept/label drift): distribution shifts that degrade model performance post-training.

### Physical transport drift modeling for label transfer

A drift-aware label-transfer framework requires: (1) a motion model, (2) uncertainty quantification, and (3) interfaces to raster/geospatial outputs compatible with SAR patch extraction.

Recommended core approach: Lagrangian particle ensembles.
Deploy an ensemble of particles seeded from the optical label geometry at t0, advected under currents plus windage, with diffusion to reflect unresolved turbulence and model error. OpenDrift is explicitly designed for trajectories and fate of drifting objects/substances, and is widely used/referenced as a generic trajectory framework. [29]

Alternative engines to keep in scope: - Parcels[30]: highly customizable Lagrangian simulation for particle tracking using gridded circulation outputs; strong academic adoption and flexibility for custom kernels (windage, beaching, etc.). [31]
- NOAA GNOME[32]: mature trajectory modeling environment historically for oil/chemicals, with robust technical documentation and GIS outputs; can be adapted conceptually for debris drift, but it is less “Python-native” than OpenDrift/Parcels for ML pipeline integration. [33]
- Operational/commercial benchmark inspiration: OPAT provides an “alert & tracking” concept that forecasts drift over 24–48 hours using Copernicus Marine products, useful as a reference architecture even if not adoptable directly for research workflows. [34]

Validation data options for transport drift: - The NOAA Global Drifter Program[35] provides access to large-scale drifter data streams and archives, valuable for plausibility checking of current/wind forcing and for calibrating dispersion/windage parameters. [36]
- Recent marine-plastic drift work (e.g., DEEP-PLAST) demonstrates integrated detection + currents/winds drift prediction, reinforcing the relevance of coupling EO detections with environmental forcing, while also highlighting the importance of quantitative validation regimes. [37]

### ML drift detection and monitoring methods

In post-training monitoring, three drift families matter:

- Data drift (covariate shift): changes in input distributions (e.g., sea state regimes, incidence angles, geographic transfer).

- Concept drift: changes in the mapping from input → label (e.g., new confusers, changing debris appearance).

- Label drift / label shift: changes in the class prior p(y) (e.g., seasonal debris frequency changes). [38]

Because the project’s outputs are segmentation maps (high-dimensional), the monitoring layer should combine: 1) tests on low-dimensional summaries (e.g., predicted debris fraction per scene), and
2) tests on feature embeddings (e.g., SSL encoder features or penultimate-layer embeddings), which are more stable than raw pixels but sensitive to distribution changes.

Key tools to operationalize drift monitoring (and what they are good at): - Alibi Detect: supports online/offline drift detectors for tabular, text, images, and time series; supports both TF and PyTorch backends; explicitly focused on drift/outlier detection. [39]
- River: provides streaming ML components including concept drift detectors (e.g., ADWIN, EDDM) suitable for scalar monitoring signals generated from the ML system. [40]
- NannyML: provides open-source monitoring with drift detection and performance estimation without immediate targets; however, its out-of-the-box focus is tabular classification/regression, implying segmentation use will require custom feature extraction and mapping to tabular proxies. [41]

How to evaluate drift detectors (so monitoring is not guesswork):
Recent benchmarking discussions emphasize metrics such as detection accuracy, detection time, and delay; these map well to engineering success criteria (false alarms vs missed detections vs lag). [42]

### Label generation approaches suited to this project

Given the central constraint (“few/no SAR ground truth”), label creation must explicitly handle uncertainty and noise.

Heuristics / weak supervision (programmatic labeling).
Snorkel’s “labeling functions” formalism is a strong fit when multiple weak signals exist (thresholds, shape priors, anomaly detectors, cross-sensor similarity scores). It enables combining noisy sources into probabilistic labels, and is grounded in peer-reviewed work. [43]

Active learning (human-in-the-loop sample selection).
Deep active learning surveys emphasize that iterative query strategies (uncertainty/diversity) can reduce labeling costs significantly, which matches the project’s need to spend human effort only where drift uncertainty is high or SAR signature is ambiguous. [44]

Self-supervision / semi-supervision for SAR.
Self-supervised pretraining for EO (SSL4EO-S12) and SAR-specific SSL methods improve representation quality with limited labels—supporting the proposal’s staged SSL → finetune plan. [45]

Label quality auditing and noise handling.
Given that drift-transferred labels will be imperfect, label-noise estimation and cleaning is valuable. “Confident learning” (cleanlab) provides methods to identify likely mislabeled instances, supporting systematic dataset improvement rather than ad hoc relabeling. [46]

Annotation tooling.
Label Studio[47] is an appropriate base tool for image segmentation/bounding boxes with support for project configuration and ML-assisted workflows in practice. [48]

## Proposed drift-aware label creation strategy and monitoring architecture

This section provides concrete candidate strategies, an end-to-end workflow, and a recommended “default” design.

### Candidate strategies for generating SAR labels

The strategies below are designed to be mix-and-match, not mutually exclusive.

| Strategy | Summary | Advantages | Limitations / failure modes | Best use |
| --- | --- | --- | --- | --- |
| Transport-only label transfer | Use drift engine to move optical labels to SAR time; label SAR within predicted uncertainty region manually | Fast to start; leverages existing optical labels; minimal ML engineering | Manual SAR searching is hard; label noise grows rapidly with Δt; hard to scale | Bootstrapping an initial SAR “gold set” for model training |
| Transport + cross-modal matching | Drift defines SAR search window; a Siamese/cross-modal embedding model ranks candidate SAR patches most similar to the optical patch | Reduces human search; scales better; directly matches the progress update’s Siamese CNN idea | Requires paired training data for the matcher (low Δt); risk of shortcut learning / confusers | Main production path for building large SAR training sets (after seed set exists) |
| Transport + weak supervision + label model | Define multiple labeling functions (SAR anomaly cues, texture, wind regime constraints, similarity scores, etc.) and combine via Snorkel into probabilistic labels | Explicitly models and denoises weak signals; scalable; supports probabilistic training labels | LF design can be time-consuming; must validate LF performance; may struggle if SAR signatures are extremely weak | Scaling beyond what humans can label; generating “silver labels” |
| Active learning loop on SAR segmentation model | Train early SAR model; use uncertainty sampling to choose new drift-seeded candidates for manual confirmation; iterate | Most annotation-efficient over time; naturally handles changing distributions | Requires initial model; needs disciplined tracking/versioning | Weeks 6+ once first SAR model exists |

Snorkel’s probabilistic labeling approach motivates using multiple weak cues rather than a single rule. [49]
Active learning is a strong fit for controlling annotation costs in segmentation-heavy settings. [44]

### Recommended end-to-end workflow

The recommended architecture treats drift + labeling + monitoring as one coherent system.

A. Data ingestion + standardization - Ingest Sentinel-2 L2A scenes and labeled optical datasets (e.g., MARIDA) and (when licensed) higher-revisit sources such as Planet-like imagery. [50]
- Ingest Sentinel-1 SLC scenes for matched times; note operational continuity across Sentinel-1A/Sentinel-1C. [51]
- Ingest Copernicus Marine winds/currents with an hourly cadence matching the drift propagation time steps. [21]

B. Transport drift engine - Implement with OpenDrift first (fastest to integrate in Python with existing ocean drift focus). [52]
- Model: currents + windage + diffusion; output an ensemble distribution at SAR time. - Export outputs as: - (1) uncertainty ellipse / bounding box (for annotation UI), and - (2) probability raster (for automated candidate mining).

C. SAR candidate mining inside drift uncertainty region A minimum viable candidate miner should not attempt full SAR detection immediately; it should provide ranking and visual guidance:

- Compute a SAR “candidate score” using a small set of cues:

- intensity anomaly statistics (relative to local neighborhood),

- texture features (e.g., GLCM-like measures),

- geometry priors (elongated slick-like shapes where applicable),

- exclusion masks (shipping lanes / persistent bright targets) where known.

- In parallel, train a cross-modal patch matcher on low Δt pairs to rank candidates (progress update’s Siamese CNN plan).

D. Labeling + review - Use Label Studio projects configured for: - bounding boxes for coarse localization, and - polygon/brush masks for fine segmentation when required. [48]
- Human task design is crucial: - always show the optical reference patch, - show drift probability overlay, - show SAR-derived candidate heatmap, - force annotators to select confidence (high/medium/low) to encode label uncertainty.

E. Training loop - Maintain three label tiers: - Gold: in-situ/controlled drops or very low Δt confirmed matches - Silver: drift + human-confirmed bounding boxes or masks - Bronze: weak labels / pseudo labels used only in semi-supervised training
- For SSL and segmentation fine-tuning, maintain strict dataset versioning to track improvements (recommended even for research).

F. Monitoring and retraining triggers - Continuous monitoring (per acquisition day/week): - Drift-engine residuals (distance between predicted and observed optical follow-up when available) - Data drift in SAR embeddings (Alibi Detect) - Scalar drift signals (predicted debris area, mean confidence) with River ADWIN/EDDM - Retraining triggers: - sustained drift alarms over N scenes - a statistically significant label shift (changed predicted debris prevalence) combined with increased uncertainty - degradation on a rolling “gold” evaluation set when available
Alibi Detect’s scope across images/time series supports the embedding-based approach. [53]
River’s ADWIN/EDDM are appropriate for scalar monitoring streams. [54]

### Comparison table of candidate methods and tools

This table emphasizes “fitness to purpose” for this project (ocean transport + SAR label bootstrapping + segmentation + monitoring).

| Component | Candidate | Pros | Cons | Effort | Maturity |
| --- | --- | --- | --- | --- | --- |
| Transport drift engine | OpenDrift | Ocean-drift focus; Python-first; particle ensemble modeling; strong documentation and references [52] | Requires parameter tuning (windage/diffusion); quality depends on forcing fields [55] | M | Widely used (research/ops) |
| Transport drift engine | Parcels | Very flexible kernel model; strong scientific adoption; designed for circulation-model outputs [56] | More engineering for “out-of-box” debris use cases; still needs calibration | M–H | Widely used (research) |
| Transport drift engine | NOAA GNOME | Mature trajectory modeling; strong technical manuals; GIS-friendly outputs [33] | Less ML-pipeline-native; debris-specific modeling may require adaptation | H | Mature (operational) |
| Operational reference | OPAT (Geomatys / ESA) | Demonstrates drift forecasting + EO alerting concept (24–48h) with Copernicus Marine forcing [57] | Not necessarily open or research-modifiable; may be platform-bound | L (as reference) | Operational service (vendor) |
| Optical baseline labels | MARIDA | Public benchmark; includes confusers; supports segmentation baselines [18] | Optical-only; SAR transfer needs drift + matching | L | Mature (research benchmark) |
| Optical detection cue | FDI + PI | Established indices for floating materials/plastic targets in Sentinel-2 contexts [22] | Still confounded by algae/foam; not SAR-direct | L | Mature (research) |
| Weak supervision | Snorkel | Labeling functions + probabilistic label model; strong published foundations [58] | Designing good LFs is non-trivial; needs gold set for validation | M | Mature (industry + research) |
| Annotation platform | Label Studio | Open-source labeling with segmentation support and ML-assisted workflows [48] | Geospatial UX customization may be needed for map-native workflows | M | Mature (production OSS) |
| Drift detection (images) | Alibi Detect | Designed for drift/outlier; supports images/time series; multiple detectors [39] | Packaging/license constraints (“source-available”); detector selection needs experimentation | M | Mature (broad adoption) |
| Drift detection (streaming scalars) | River | Lightweight online drift detectors; good for scalar KPIs [54] | Not image-native; must engineer summary signals | L–M | Mature (OSS) |
| Label quality audit | cleanlab (confident learning) | Systematic identification of label issues; supports data-centric iteration [46] | Requires probabilistic predictions and careful interpretation | M | Mature (research + OSS) |
| Label shift detection | BBSE (Lipton et al.) | Principled test/estimation for label shift; useful if prevalence changes [59] | Assumptions (invertible confusion matrix; stable p(x | y)) may not hold strongly | M |

## Evaluation metrics and success criteria

Because labels are being created via an uncertain transfer, evaluation must address (1) transport accuracy, (2) label correctness, and (3) monitoring reliability.

### Drift engine evaluation

Primary metrics (per matched event): - Position error: great-circle distance error and/or RMSE between predicted patch centroid and observed centroid (the progress update’s plan). (Progress update: Pretorius, 2026)
- Uncertainty calibration: fraction of observed centroids that fall inside the predicted 50% / 90% uncertainty region (coverage probability).
- Skill vs baselines: compare against “no motion” and “current-only” baselines to show the value of windage and diffusion.

To enable quantitative evaluation, include real drifter/instrumented targets where possible (NOAA drifters for sanity checks; project-specific low-cost drifters for local truthing). [36]

### SAR label-quality evaluation

A robust label-quality program should include:

- Gold audit set: a small set of SAR scenes/patches manually labeled by expert(s) without drift hints (or with controlled target drops) to serve as an unbiased measure.

- Agreement measures: inter-annotator agreement on bounding boxes/masks for a subset (especially important for ambiguous SAR signatures).

- Noise detection: run label-issue detection (confident learning) on the training set routinely to identify systematic label failures tied to conditions (wind regime, incidence geometry, geography). [46]

- Label provenance tracking: store for every label its origin (in-situ vs drift-transfer vs weak label), Δt, forcing fields summary, and annotator confidence.

Success criteria (label quality) should be expressed in ranges because true difficulty is unknown. A reasonable initial target for “silver” labels is: - ≥80% correctness for coarse localization (is the patch inside the box?), and - ≥65–75% correctness for fine segmentation masks (IoU against gold), improving across iterations.

### Drift detection evaluation (ML monitoring)

Drift detectors should be tested on replayed historical streams (or simulated perturbations) and scored via: - false alarm rate, - detection delay, - sensitivity to known regime changes (e.g., seasonal sea-state change). [42]

Monitoring should be defined as successful only if it provides actionable triggers with acceptable false positives (otherwise it creates “alert fatigue”).

## Implementation plan with milestones, timeline, resourcing, risks, and next steps

### Assumptions and unknowns

The documents do not specify several planning-critical parameters; the plan therefore assumes: - unknown number of SAR scenes and matchable label events, - unknown number of classes (binary vs multi-class), - unknown annotation budget and number of annotators, - unknown compute environment (local GPU vs cloud), - unknown availability and cadence of in-situ deployments.
(Proposal: Pretorius, 2025; Progress update: Pretorius, 2026)

All estimates below are expressed as formulas or ranges.

### Milestones and week-level timeline

The schedule below is designed for a ~16-week execution window; adjust length based on thesis deadlines and field constraints.

gantt
    title Drift-aware label creation and monitoring (16-week plan)
    dateFormat  YYYY-MM-DD
    axisFormat  %d-%b

    section Foundations
    Define label schema, QA rules, splits          :a1, 2026-03-11, 10d
    Data inventory + reproducible preprocessing    :a2, after a1, 15d

    section Drift engine
    Implement OpenDrift baseline + IO interfaces   :b1, 2026-04-01, 15d
    Calibrate parameters (windage/diffusion)       :b2, after b1, 10d
    Optical-based drift validation harness         :b3, after b1, 12d

    section Label creation
    Low-Δt manual SAR matching (seed gold set)     :c1, 2026-04-15, 15d
    Candidate mining + UI integration (Label Studio):c2, after c1, 12d
    Cross-modal matcher prototype (Siamese)        :c3, after c1, 15d

    section Model training loop
    Train first SAR segmenter (baseline U-Net)     :d1, 2026-05-20, 12d
    Active learning iteration (1–2 cycles)         :d2, after d1, 15d
    Label quality audit + cleanlab pass            :d3, after d1, 10d

    section Monitoring & deployment artifacts
    Drift monitoring dashboards + alerts           :e1, 2026-06-10, 12d
    Retraining triggers + model registry           :e2, after e1, 8d
    Final evaluation + reporting                   :e3, after e2, 10d

Key dependencies: - Cross-modal matching (Siamese) depends on having enough low-Δt paired examples. - Monitoring design depends on stable “signals” extracted from the inference pipeline (debris fraction, embedding stats).

### Resource estimates

Storage
A practical planning heuristic: - Sentinel-1 IW SLC ≈ 8 GB/product (typical) → storage scales quickly with number of acquisitions. [28]
- Store at least three tiers: raw scenes, processed features (if cached), and patch datasets.

A simple estimate: - S_total ≈ N_scenes * (S_raw + S_processed_cache) + N_patches * S_patch - If processed cache is avoided (recompute-on-demand), storage drops but compute rises.

Compute (training)
Compute needs depend on patch counts, feature stack width (VV/VH + derived bands + biophysical stack), and model size: - Baseline U-Net training can be done on a single modern GPU if patch counts are moderate, but SSL pretraining and large-scale fine-tuning benefit from multi-GPU or long runtimes. SSL4EO-style pretraining is explicitly motivated by large unlabeled corpora. [24]
- Drift simulation cost is usually modest compared to deep learning training (particle ensembles are CPU-friendly but scale with ensemble size and number of seeds). [52]

Annotation effort
Define annotation as two stages: 1) confirm presence/absence inside drift box (fast), then 2) (if present) draw accurate mask (slow).

Use scenario planning: - If N_candidates candidates are reviewed at t_box minutes each, plus N_masks masks at t_mask minutes each:
Hours ≈ (N_candidates*t_box + N_masks*t_mask) / 60.

Active learning should reduce N_candidates over cycles by focusing on ambiguous/high-value patches. [60]

### Risks and mitigations

| Risk | Why it matters | Mitigation |
| --- | --- | --- |
| Drift uncertainty too large for useful SAR search (high Δt, poor forcing) | Bounding boxes grow; SAR search becomes impractical | Split regimes by Δt; focus on low/medium Δt first; add higher revisit optical (Planet-class) as “bridge”; use ensemble calibration with drifters [61] |
| SAR signatures too weak or confusable | Label noise increases; training collapses | Introduce multi-class confusers (from optical datasets like MARIDA); enforce strict gold audit set; incorporate biophysical context into model inputs [62] |
| Weak supervision rules overfit and create systematic bias | Model learns artifacts; poor generalization | Use Snorkel probabilistic labels + gold validation; track LF coverage/conflict; retire poor LFs [49] |
| Monitoring produces too many false alarms | Operationally unusable; wasted time | Evaluate detectors with detection delay/false alarm metrics; require persistence criteria (K-of-N rule) [63] |
| Data volume overwhelms storage/IO | Pipeline becomes fragile | Patch-first strategy; avoid caching everything; compress intermediate rasters; prioritize scenes with label utility (matched times) [28] |

### Success criteria

This project needs explicit, measurable “done” conditions:

Transport drift model - For low/medium Δt cases: median centroid error below a project-defined threshold (set after pilot; report as meters/km), and calibrated uncertainty regions (e.g., 90% region contains ≥80–90% of observed centroids). (Progress update: Pretorius, 2026)

Label creation - A gold set of at least O(50–200) SAR patches (size depends on feasibility) with expert-reviewed masks. - A silver set ≥5× larger than gold, with provenance recorded and label-noise audits performed. [46]

SAR detection model - Demonstrable improvement across iterations on gold set using segmentation metrics (mIoU/Dice/F1) and calibrated uncertainty; the exact threshold must be set after the first baseline run because task difficulty is unknown. [64]

Monitoring - Drift alarms correlate with measurable changes (distribution shifts or degraded performance) and maintain an acceptable false alarm rate under retrospective testing. [65]

### Recommended next steps

1) Freeze the label schema (binary vs multi-class, mask vs box) and define annotation rules and QA checks before scaling any labeling. [66]
2) Implement an OpenDrift prototype that outputs (a) uncertainty boxes and (b) probability rasters, and validate quickly on optical-to-optical transitions (S2→S2 or Planet→Planet) before attempting SAR transfer. [67]
3) Build a small gold SAR set from low Δt matches (manual search starting at the optical location) to anchor both the cross-modal matcher and the first SAR detector. (Progress update: Pretorius, 2026)
4) Stand up Label Studio with drift overlays, and begin capturing provenance + annotator confidence from day one. [68]
5) Add drift monitoring signals early (even before model maturity) so baseline distributions are recorded and later changes can be detected reliably. [69]

## References

Pretorius, J. (2025) Developing a synthetic aperture radar-based dataset and machine learning model for the detection of floating marine plastics in the South African exclusive economic zone. Research proposal (unpublished), University of Pretoria[12].

Pretorius, J. (2026) Progress Report (19/02/2026). Progress update document (unpublished).

Biermann, L. et al. (2020) ‘Finding Plastic Patches in Coastal Waters using Optical Satellite Data’, Scientific Reports, 10, article 5364. DOI: 10.1038/s41598-020-62298-z. [70]

Kikaki, K. et al. (2022) ‘MARIDA: A benchmark for Marine Debris detection from Sentinel-2 remote sensing data’, PLOS ONE, 17(1), e0262247. DOI: 10.1371/journal.pone.0262247. [71]

Themistocleous, K. et al. (2020) ‘Investigating Detection of Floating Plastic Litter from Space using Sentinel-2 Imagery’, Remote Sensing, 12(16), 2648. DOI: 10.3390/rs12162648. [72]

Dagestad, K.-F. et al. (2017) ‘OpenDrift v1.0: a generic framework for trajectory modeling’, (technical paper/report). [73]

Delandmeter, P. and van Sebille, E. (2019) ‘The Parcels v2.0 Lagrangian framework’, Geoscientific Model Development, 12, 3571–3588. DOI: 10.5194/gmd-12-3571-2019. [74]

Cernian, A. and Iliuta, M.-E. (2025) ‘The DEEP-PLAST approach to marine plastic detection and trajectory prediction for the Black Sea’, Water, 17(22), 3318. DOI: 10.3390/w17223318. [37]

Ratner, A. et al. (2017) ‘Snorkel: Rapid Training Data Creation with Weak Supervision’, arXiv:1711.10160. [75]

Ratner, A. et al. (2019) ‘Snorkel: rapid training data creation with weak supervision’, Journal of Machine Learning Research / system paper (PMC version). [76]

Hinder, F. et al. (2024) ‘One or two things we know about concept drift—a survey…’, Frontiers in Artificial Intelligence. [77]

Lipton, Z.C., Wang, Y.-X. and Smola, A. (2018) ‘Detecting and Correcting for Label Shift with Black Box Predictors’, Proceedings of ICML (PMLR). [78]

Northcutt, C.G. et al. (2021/2022 versions) ‘Confident Learning’, arXiv:1911.00068. [79]

Wang, Y. et al. (2022/2023) ‘SSL4EO-S12…’, arXiv:2211.07044 / IEEE GRSM software+dataset article. [80]

Oktay, O. et al. (2018) ‘Attention U-Net’, arXiv:1804.03999. [23]

Official documentation and product pages (URLs provided in the citations): OpenDrift, Parcels, Copernicus Marine products, Sentinel mission pages, Label Studio docs, Alibi Detect, River, NannyML, NOAA Global Drifter Program. [81]

[1] [46] [79] https://arxiv.org/pdf/1911.00068

https://arxiv.org/pdf/1911.00068

[2] [4] [28] https://www.mdpi.com/2072-4292/13/22/4622

https://www.mdpi.com/2072-4292/13/22/4622

[3] [29] [52] [67] [81] https://opendrift.github.io/

https://opendrift.github.io/

[5] [10] [22] [70] https://www.nature.com/articles/s41598-020-62298-z

https://www.nature.com/articles/s41598-020-62298-z

[6] [36] [61] https://www.aoml.noaa.gov/global-drifter-program/

https://www.aoml.noaa.gov/global-drifter-program/

[7] [12] [16] [32] [39] [53] [69] https://docs.seldon.ai/alibi-detect

https://docs.seldon.ai/alibi-detect

[8] [44] [60] https://arxiv.org/pdf/2405.00334

https://arxiv.org/pdf/2405.00334

[9] [35] [42] [63] [65] https://www.mdpi.com/1999-5903/15/5/169

https://www.mdpi.com/1999-5903/15/5/169

[11] [18] [25] [50] [62] [64] [66] [71] https://journals.plos.org/plosone/article?id=10.1371%2Fjournal.pone.0262247

https://journals.plos.org/plosone/article?id=10.1371%2Fjournal.pone.0262247

[13] [54] https://riverml.xyz/0.7.0/api/drift/ADWIN/

https://riverml.xyz/0.7.0/api/drift/ADWIN/

[14] [48] https://labelstud.io/guide/get_started.html

https://labelstud.io/guide/get_started.html

[15] [37] [47] https://www.mdpi.com/2073-4441/17/22/3318

https://www.mdpi.com/2073-4441/17/22/3318

[17] [30] [43] [58] [75] https://arxiv.org/abs/1711.10160

https://arxiv.org/abs/1711.10160

[19] https://documentation.dataspace.copernicus.eu/Data/Sentinel1.html

https://documentation.dataspace.copernicus.eu/Data/Sentinel1.html

[20] https://sentinels.copernicus.eu/sentinel-data-access/sentinel-products/sentinel-2-data-products/collection-1-level-2a

https://sentinels.copernicus.eu/sentinel-data-access/sentinel-products/sentinel-2-data-products/collection-1-level-2a

[21] https://data.marine.copernicus.eu/product/GLOBAL_ANALYSISFORECAST_PHY_001_024/description

https://data.marine.copernicus.eu/product/GLOBAL_ANALYSISFORECAST_PHY_001_024/description

[23] https://arxiv.org/abs/1804.03999

https://arxiv.org/abs/1804.03999

[24] [45] [80] https://arxiv.org/abs/2211.07044

https://arxiv.org/abs/2211.07044

[26] https://eo4society.esa.int/projects/mireia/

https://eo4society.esa.int/projects/mireia/

[27] [51] https://www.esa.int/Applications/Observing_the_Earth/Copernicus/Sentinel-1/Mission_ends_for_Copernicus_Sentinel-1B_satellite

https://www.esa.int/Applications/Observing_the_Earth/Copernicus/Sentinel-1/Mission_ends_for_Copernicus_Sentinel-1B_satellite

[31] [56] https://parcels-code.org/

https://parcels-code.org/

[33] [55] https://response.restoration.noaa.gov/sites/default/files/GNOME_Tech_Doc.pdf

https://response.restoration.noaa.gov/sites/default/files/GNOME_Tech_Doc.pdf

[34] [57] https://marine.copernicus.eu/services/use-cases/ocean-plastic-alert-tracking-system-calculating-drift-using-copernicus-marine

https://marine.copernicus.eu/services/use-cases/ocean-plastic-alert-tracking-system-calculating-drift-using-copernicus-marine

[38] [77] https://www.frontiersin.org/journals/artificial-intelligence/articles/10.3389/frai.2024.1330257/full

https://www.frontiersin.org/journals/artificial-intelligence/articles/10.3389/frai.2024.1330257/full

[40] https://riverml.xyz/0.8.0/examples/concept-drift-detection/

https://riverml.xyz/0.8.0/examples/concept-drift-detection/

[41] https://nannyml.readthedocs.io/en/latest/landing_page.html

https://nannyml.readthedocs.io/en/latest/landing_page.html

[49] [76] https://pmc.ncbi.nlm.nih.gov/articles/PMC7075849/

https://pmc.ncbi.nlm.nih.gov/articles/PMC7075849/

[59] [78] https://proceedings.mlr.press/v80/lipton18a/lipton18a.pdf

https://proceedings.mlr.press/v80/lipton18a/lipton18a.pdf

[68] https://labelstud.io/guide/

https://labelstud.io/guide/

[72] https://www.mdpi.com/2072-4292/12/16/2648

https://www.mdpi.com/2072-4292/12/16/2648

[73] https://d-nb.info/1143541367/34

https://d-nb.info/1143541367/34

[74] https://gmd.copernicus.org/articles/12/3571/2019/

https://gmd.copernicus.org/articles/12/3571/2019/