## Dashboard
Masters Tasks Tracker
Open tasks |  |  | Complete |  |  | Awaiting review |  | % complete
37 |  |  | 4 |  |  | 0 |  | 9.756%
Task status summary |  |  | Workstream progress
Status | Tasks |  | Workstream | Total |  | Open | % complete
Not started | 4 |  | Literature review | 5 | 0 | 5 | 0%
In progress | 32 |  | Data & imagery | 6 | 0 | 6 | 0%
Waiting for supervisor review | 0 |  | Fieldwork & ground truthing | 5 | 0 | 5 | 0%
Blocked | 1 |  | Methodology & modelling | 8 | 1 | 7 | 12.5%
Complete | 4 |  | Analysis & validation | 6 | 2 | 4 | 33.33%
|  |  | Thesis writing & outputs | 7 | 0 | 7 | 0%
|  |  | Admin & meetings | 4 | 1 | 3 | 25%
Milestone | Target date | Status | % complete
Project framing and thesis direction clarified |  | In progress |  | 70%
Core literature base assembled |  | In progress |  | 75%
Data inventory and scene coverage understood |  | In progress |  | 70%
Observation records and labels cleaned up |  | In progress |  | 65%
Pilot SAR processing workflow proven |  | Complete |  | 95%
Broader processing and baseline experiments underway |  | In progress |  | 60%
Initial analysis findings documented |  | In progress |  | 55%
Thesis writing pack and supervisor review material assembled |  | In progress |  | 45%

## Tasks
Masters Task Tracker
Task ID | Workstream | Task | Deliverable / definition of done | Owner | Status | Priority | Start date | Due date | % complete | Blocked? | Evidence / link | Supervisor comments | Next action | Last updated
T-001 | Literature review | Define the literature review themes | A short list of themes, concepts, and keywords that structures the review and keeps reading focused. | Joshua | In progress | High |  |  | 70% | No | Writing/; Progress_Tracker/docs/reference/ |  | Turn the current reading into a clean review outline.
T-002 | Literature review | Collect core SAR and marine-debris papers | A working reading list covering SAR theory, floating debris detection, drift context, and related remote-sensing studies. | Joshua | In progress | High |  |  | 75% | No | Writing/ShipSamples.txt; MERIA/ |  | Add any missing cornerstone papers before deeper synthesis.
T-003 | Literature review | Write short summaries for each key paper | Brief notes capturing the method, data, findings, and relevance of each paper. | Joshua | In progress | Medium |  |  | 55% | No | Writing/; Progress_Tracker/docs/reference/ |  | Standardise the format of the reading notes.
T-004 | Literature review | Identify the research gap and thesis positioning | A clear statement of what this project contributes beyond the reviewed literature. | Joshua | In progress | High |  |  | 50% | No | Progress_Tracker/docs/reference/meria_sa_slc_science_notes.md |  | Turn current notes into a concise gap statement.
T-005 | Literature review | Draft the literature review section structure | A section-by-section outline for the thesis literature review chapter. | Joshua | Not started | Medium |  |  | 20% | No | Writing/; docs/ |  | Break the review into major themes and subheadings.
T-006 | Data & imagery | Inventory all available datasets and folders | A clean view of what data exists, where it lives, and how it supports the project. | Joshua | In progress | High |  |  | 80% | No | MERIA/; MARIDA/; PlanetData/; Data_Creation/ |  | Capture any remaining unmanaged inputs and outputs.
T-007 | Data & imagery | Organise the key imagery sources | A tidy working structure for Sentinel-1, Planet, and supporting project imagery. | Joshua | In progress | High |  |  | 65% | No | Data_Creation/; PlanetData/; MERIA/ |  | Clean up the folders that are still mixing raw and processed material.
T-008 | Data & imagery | Check case-study scene coverage | A practical view of which scenes exist for the main locations and timestamps of interest. | Joshua | In progress | High |  |  | 75% | No | meria_15km_coverage_summary.csv; meria_15km_coverage_products.csv |  | Confirm which locations still need more complete coverage.
T-009 | Data & imagery | Record missing or weak imagery cases | A list of the scenes, assets, or observations that are still missing or low quality. | Joshua | In progress | Medium |  |  | 45% | No | Progress_Tracker/docs/evidence/planet/; meria_15km_coverage_summary.csv |  | Separate true data gaps from processing gaps.
T-010 | Data & imagery | Prepare the imagery acquisition workflow | A repeatable process for finding, matching, and requesting scenes when more data is needed. | Joshua | In progress | Medium |  |  | 60% | No | Scripts/; Data_Creation/build_meria_sa_s1_slc_matches.py |  | Simplify the workflow into a short checklist.
T-011 | Data & imagery | Resolve outstanding Planet acquisition gaps | A list of matched Planet scenes or a clear record of why those matches cannot yet be resolved. | Joshua | Blocked | High |  |  | 30% | Yes | Progress_Tracker/docs/evidence/planet/ocean_scan_mireia_planet_report.md |  | Unblock the API access needed to finish the Planet lookup work.
T-012 | Fieldwork & ground truthing | Consolidate observation and label records | One reliable working set of observation metadata, labels, and related identifiers. | Joshua | In progress | High |  |  | 75% | No | MERIA/; Scripts/ocean_scan_mireia_patches.geojson; Data_Creation/ |  | Check for duplicate, missing, or inconsistent records.
T-013 | Fieldwork & ground truthing | Review the quality of validation information | A clearer understanding of which observations are strong, weak, or uncertain for analysis. | Joshua | In progress | High |  |  | 60% | No | MERIA/; Progress_Tracker/docs/evidence/drift/validation_summary.json |  | Tag the cases that should be treated cautiously.
T-014 | Fieldwork & ground truthing | Standardise coordinate and location handling | Consistent coordinates, naming, and geometry handling across project datasets. | Joshua | In progress | Medium |  |  | 55% | No | Data_Creation/Ghana_Full.shp; Scripts/ocean_scan_mireia_patches.geojson |  | Confirm that the main study assets align spatially.
T-015 | Fieldwork & ground truthing | Track scene control variables | A reusable record of scene attributes such as orbit direction, incidence angle, and other comparison controls. | Joshua | In progress | High |  |  | 40% | No | Meeting Log!A5:G5; Data_Creation/process_meria_sa_slc_targets.py |  | Add these controls explicitly to the working analysis notes.
T-016 | Fieldwork & ground truthing | Review digitisation and labeling progress | A current picture of what has been digitised or curated and what still needs attention. | Joshua | In progress | Medium |  |  | 60% | No | Data_Creation/build_meria_digitisation_tracker.py; Data_Creation/MERIA_digitisation_tracker.docx |  | Use the tracker to identify the next labeling priorities.
T-017 | Methodology & modelling | Write the end-to-end methodology outline | A plain-language description of the full project workflow from data selection to outputs. | Joshua | In progress | High |  |  | 70% | No | Progress_Tracker/docs/reference/; Pipeline_notes.md |  | Condense the current technical notes into one project workflow.
T-018 | Methodology & modelling | Stabilise the SAR preprocessing workflow | A reproducible preprocessing path that can be rerun without guesswork. | Joshua | In progress | High |  |  | 80% | No | Data_Creation/process_meria_sa_slc_targets.py; sar_server_pipeline/ |  | Reduce any remaining ambiguity in the preprocessing steps.
T-019 | Methodology & modelling | Run pilot processing on representative scenes | A small set of processed scenes that proves the workflow is working on real examples. | Joshua | Complete | High |  |  | 95% | No | Progress_Tracker/docs/evidence/s1_slc/; Progress_Tracker/docs/reference/meria_sa_slc_science_notes.md |  | Use the pilot outputs as the baseline for scaling up.
T-020 | Methodology & modelling | Scale processing to more scenes | A broader processed sample that supports comparison across cases instead of only pilot examples. | Joshua | In progress | High |  |  | 60% | No | Data_Creation/meria_sa_plastic_s1_slc; Progress_Tracker/docs/evidence/s1_slc/ |  | Process the next batch of priority scenes.
T-021 | Methodology & modelling | Build the patch and feature extraction workflow | A clean route from processed imagery to analysis-ready patches or features. | Joshua | In progress | High |  |  | 75% | No | Data_Creation/build_sar_patch_library.py; Data_Creation/build_sar_library_analysis.py |  | Tighten the workflow around retained samples and outputs.
T-022 | Methodology & modelling | Define baseline experiments | A simple first set of experiments that can be explained clearly in the thesis. | Joshua | In progress | Medium |  |  | 50% | No | Progress_Tracker/docs/evidence/segmentation/summary.json; Progress_Tracker/docs/evidence/patches/ |  | Keep the baseline small enough to interpret well.
T-023 | Methodology & modelling | Run initial modelling experiments | One or more baseline experiment runs with saved outputs for later comparison. | Joshua | In progress | Medium |  |  | 45% | No | Progress_Tracker/docs/evidence/segmentation/summary.json |  | Record what worked and what clearly needs improvement.
T-024 | Methodology & modelling | Prepare the server-side processing setup | A deployment-ready workflow that can run the processing on the target server when needed. | Joshua | In progress | Medium |  |  | 65% | No | sar_server_pipeline/docs/runbook.md; sar_server_pipeline/compose.yml |  | Finish the setup path needed for a practical server run.
T-025 | Analysis & validation | Explore feature distributions | Basic plots and summaries showing how important variables behave across classes or cases. | Joshua | Complete | High |  |  | 90% | No | Progress_Tracker/docs/evidence/patches/plastic_feature_distributions.png |  | Use the outputs to decide which features deserve emphasis.
T-026 | Analysis & validation | Compare separability between important classes | A first check of whether the main classes look distinguishable in the available features. | Joshua | Complete | High |  |  | 85% | No | Progress_Tracker/docs/evidence/patches/ghana_plastic_vs_other_feature_importance.csv |  | Turn the most useful comparisons into thesis-ready talking points.
T-027 | Analysis & validation | Validate drift outputs against detections | A straightforward comparison between modeled drift positions and observed detections. | Joshua | In progress | High |  |  | 70% | No | Progress_Tracker/docs/evidence/drift/drift_summary.json; Progress_Tracker/docs/evidence/drift/validation_summary.json |  | Write down what the drift validation does and does not show.
T-028 | Analysis & validation | Review model success and failure cases | A visual review of where the baseline behaves well and where it breaks down. | Joshua | In progress | Medium |  |  | 45% | No | Progress_Tracker/docs/evidence/segmentation/ |  | Summarise the most instructive failure patterns.
T-029 | Analysis & validation | Document the main findings from the first analyses | Short written findings that can be reused directly in the thesis or presentations. | Joshua | In progress | High |  |  | 40% | No | Progress_Tracker/docs/evidence/patches/; Progress_Tracker/docs/evidence/drift/; Progress_Tracker/docs/evidence/segmentation/ |  | Translate outputs into simple claims with caveats.
T-030 | Analysis & validation | Define the final evaluation checklist | A compact checklist for deciding whether a result is ready to report. | Joshua | Not started | Medium |  |  | 15% | No | Progress_Tracker/docs/evidence/; docs/ |  | List the exact checks to apply before claiming a result.
T-031 | Thesis writing & outputs | Draft the thesis chapter structure | A full chapter outline covering introduction, literature, data, methods, results, and discussion. | Joshua | In progress | High |  |  | 60% | No | Writing/; docs/ |  | Lock the chapter order and subsection names.
T-032 | Thesis writing & outputs | Write the methods chapter draft | A readable first draft of the methods chapter based on the workflow already built. | Joshua | In progress | High |  |  | 55% | No | Progress_Tracker/docs/reference/; sar_server_pipeline/docs/runbook.md |  | Start converting technical notes into thesis prose.
T-033 | Thesis writing & outputs | Draft the data and study-area sections | A thesis-ready explanation of the datasets, study areas, and supporting metadata. | Joshua | Not started | High |  |  | 25% | No | MERIA/; Data_Creation/; Progress_Tracker/docs/reference/ |  | Use the current data inventory as the basis for this section.
T-034 | Thesis writing & outputs | Draft the results section | An early write-up of the main results using the strongest current outputs. | Joshua | Not started | High |  |  | 20% | No | Progress_Tracker/docs/evidence/ |  | Pick the minimum set of results needed for a first draft.
T-035 | Thesis writing & outputs | Curate figures and tables for the thesis | A shortlist of visuals and tables that are clean enough to use in the written thesis. | Joshua | In progress | High |  |  | 50% | No | Progress_Tracker/docs/evidence/patches/; Progress_Tracker/docs/evidence/segmentation/; Progress_Tracker/docs/evidence/drift/ |  | Select the strongest visuals and start drafting captions.
T-036 | Thesis writing & outputs | Prepare a supervisor review pack | A manageable set of notes, figures, and status points for a productive review conversation. | Joshua | In progress | Medium |  |  | 45% | No | Progress_Tracker/docs/evidence/; Progress_Tracker/docs/reference/ |  | Package the current state into something easy to review.
T-037 | Thesis writing & outputs | Maintain reproducibility notes and appendices | Supporting notes that explain how the work was run and what the key outputs mean. | Joshua | In progress | Medium |  |  | 65% | No | sar_server_pipeline/docs/runbook.md; Progress_Tracker/docs/reference/ |  | Keep the support material aligned with the current workflow.
T-038 | Admin & meetings | Keep the masters tracker up to date | A tracker that reflects the real state of the MSc project at a useful level of detail. | Joshua | Complete | High |  |  | 100% | No | C:/Users/Joshua Pretorius/Downloads/Joshua_Msc_Task.xlsx |  | Use this tracker as the main planning view going forward.
T-039 | Admin & meetings | Prepare talking points before supervisor meetings | A short agenda and decision list ready before each meeting. | Joshua | In progress | Medium |  |  | 40% | No | Meeting Log!A5:G5 |  | List the open questions and decisions needed next.
T-040 | Admin & meetings | Record actions and decisions after meetings | An updated meeting log with follow-up actions clearly captured. | Joshua | In progress | Medium |  |  | 35% | No | Meeting Log!A5:G5 |  | Keep the log current after each supervisor discussion.
T-041 | Admin & meetings | Break the next phase into weekly priorities | A short rolling priority list that helps move from broad project goals to immediate work. | Joshua | In progress | Medium |  |  | 30% | No | Joshua_Msc_Task_populated.xlsx |  | Turn the highest-priority open tasks into the next weekly plan.

## Milestones
Masters Milestones
Milestone | Workstream | Target date | Status | % complete | Notes
Project framing and thesis direction clarified | Literature review |  | In progress | 70% | The project direction is visible, but the research gap and positioning still need tightening.
Core literature base assembled | Literature review |  | In progress | 75% | Key reading material exists, but summaries and synthesis still need to be formalised.
Data inventory and scene coverage understood | Data & imagery |  | In progress | 70% | Most of the relevant data sources are known, but some scene and acquisition gaps remain.
Observation records and labels cleaned up | Fieldwork & ground truthing |  | In progress | 65% | Ground-truth and label assets exist, but consistency checks are still needed.
Pilot SAR processing workflow proven | Methodology & modelling |  | Complete | 95% | Representative scenes have already been processed successfully and can anchor the next phase.
Broader processing and baseline experiments underway | Methodology & modelling |  | In progress | 60% | The pipeline exists, but it still needs to be extended and used consistently across more cases.
Initial analysis findings documented | Analysis & validation |  | In progress | 55% | Several useful outputs exist, but the findings are not yet fully written up in a coherent way.
Thesis writing pack and supervisor review material assembled | Thesis writing & outputs |  | In progress | 45% | There is enough material to start packaging drafts, figures, and review notes more deliberately.

## Meeting Log
Supervisor Meeting Log
Meeting date | Agenda / objective | Notes | Actions agreed | Due date | Status | Next meeting / notes
2026-06-25 | Progress Update. | Create task tracker. Take note of orbit direction and incident angle/control for these variables. Transfrom scripts to run as docker images on server. | Create docker scripts and have repo ready for Server - Joshua | 2026-07-01 | In progress | Tuesday - 30th June