## Gantt Chart
End Date
Joshua Msc GANTT CHART
PROJECT TITLE |  | Developing a Synthetic Aperture Radar based dataset and machine learning model for the detection of Floating Marine Plastics in the South African Exclusive Economic Zone
Due Date |  | 2026-08-30
Task Number | TASK TITLE | START DATE | PLANNED DUE DATE | PCT OF TASK COMPLETE | 2025-06-25 | [19 empty] | 2025-07-25 | [19 empty] | 2025-08-25 | [19 empty] | 2025-09-25 | [19 empty] | 2025-10-25 | [19 empty] | 2025-11-25 | [19 empty] | 2025-12-25
[5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 22 |  |  |  |  | WEEK 23 |  |  |  |  | WEEK 24 |  |  |  |  | WEEK 25 |  |  |  |  | WEEK 26 |  |  |  |  | WEEK 27 |  |  |  |  | WEEK 28
[5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | T | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Proposal
1.1 | Project Definition |  |  | 100% | bar: WEEK 1 M to WEEK 1 T; WEEK 6 F
1.2 | Proposal Section 1 |  |  | 100% | bar: WEEK 1 M to WEEK 2 F; WEEK 6 F
1.3 | Proposal Section 2 |  |  | 100% | bar: WEEK 2 M to WEEK 3 F; WEEK 6 F
1.4 | Proposal Section 3 |  |  | 100% | bar: WEEK 2 M to WEEK 4 F; WEEK 6 F
1.5 | Proposal Submission | 2025-06-01 | 31/06/2025 | 100% | bar: WEEK 2 M to WEEK 2 R; WEEK 4 F; WEEK 6 F
2 | Data Streams
2.1 | Extract MARDIA with script |  |  | 100% | bar: WEEK 5 M to WEEK 5 W; WEEK 6 F to WEEK 7 R
2.2 | Create MARIDA Positive pairs (S1 and S2) |  |  | 25% | bar: WEEK 6 F to WEEK 8 R
2.3 | Define drift model and matching models to extract MARIDA on S1 |  |  | 100% | bar: WEEK 6 F to WEEK 9 F
2.4 | Extract MIRIEA with script |  |  | 25%
2.5 | Create DFFE dataset |  |  | 10% | bar: WEEK 4 F; WEEK 6 F
2.5 | Biophysical variables |  |  | 75% | bar: WEEK 6 M to WEEK 6 W; WEEK 6 F
3 | Model Architecture
3.1 | Define Architecture (eg unet) |  |  | 100%
3.2 | Write model pipeline and layers |  |  | 50% | bar: WEEK 6 W to WEEK 6 F
3.3 | Define patch sizes and channels |  |  | 75% | bar: WEEK 6 F
3.4 | Increse complexity iteratively (Attention Gates) |  |  | 0% | bar: WEEK 6 F
4 | Processing Pipelines
4.1 | Preprocessing Pipelines |  |  | 90% | bar: WEEK 1 M to WEEK 3 F; WEEK 5 T to WEEK 5 F; WEEK 6 F
4.2 | Model pipelines |  |  | 25% | bar: WEEK 6 R to WEEK 9 W
4.3 | Patch Extraction Pipelines |  |  | 0% | bar: WEEK 6 F
5 | Model Training
5.1 | Initail General SSL |  |  | 100% | bar: WEEK 6 R to WEEK 6 F
5.2 | Localised SSL (SA Marine Scenes) and wind layers |  |  | 0% | bar: WEEK 6 F
5.3 | Fine Tuning on Labelled data |  |  | 0% | bar: WEEK 6 F
5.4 | Calcuate Training Validation and Loss |  |  | 0% | bar: WEEK 6 F
6 | Model Application
6.1 | Define dates for application aligned with plastic events |  |  | 0% | bar: WEEK 6 F
6.2 | Apply trained model in study areas |  |  | 0% | bar: WEEK 6 F
6.3 | Map Detected Plastics |  |  | 0% | bar: WEEK 6 F
6.4 | Validate Detections |  |  | 0% | bar: WEEK 6 F
7 | Final Writing
7.1 | Finalise Literature Review |  |  | 0% | bar: WEEK 6 F
7.2 | Methods |  |  | 0% | bar: WEEK 6 F
7.3 | Results |  |  | 0% | bar: WEEK 6 F
7.4 | Discussion |  |  | 0% | bar: WEEK 6 F
Conclusion | bar: WEEK 6 F
8 | Article Preperation and Submission
8.1 | Dataset Paper for submission to Journal |  |  | 0% | bar: WEEK 6 F
8.2 | Deep Learning SAR Journal Paper |  |  | 0% | bar: WEEK 6 F
8.3 | Notify department with intent to submit |  |  | 0% | bar: WEEK 6 F
8.4 | Final Submssion |  |  | 0% | bar: WEEK 6 F